## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team and Freshman Seminar acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2171-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions, cross-team testing, and Freshman Seminar testing.
Team Name | 2208-swen-261-01 CDI
Testing Team Name | fill in when doing cross-team or Freshman Seminar testing

## Test Plan
| Acceptance Criterion | Sprint 1 | Tester initials; date; comments (required if test failed) | Sprint 2 | Tester initials; date; comments (required if test failed) | Sprint 3 | Tester initials; date; comments (required if test failed)
As a Player I want to sign-in so that I can play a game of checkers. | Given that I have not yet signed in when I see the Home page then I must see a means to sign-in. (such as a link or button) | Pass | ND, 6/27/2021 | Pass | MS, 7/14/21 | Pass | EL + ZM; 07/22/21
| Given that I am not signed-in when I do click on the sign-in link then I expect to be taken to the Sign-in page, with a means to enter a player name. | Pass | JI, 6/27/2021 | Pass | MS, 7/14/21 | Pass | EL + ZM; 07/22/21
| Given that no one else is using my name when I enter my name containing at least one alphanumeric character and optionally spaces in the sign-in form and click the Sign-in button then I expect the system to reserve my name and navigate back to the Home page. | Pass | JI, 6/27/2021 | Pass | MS, 7/14/21 | Pass | EL + ZM; 07/22/21
| Given that I am on the Sign-in page when I enter a name that does not contain at least one alphanumeric character or contains one or more characters that are not alphanumeric or spaces and click the Sign-in button then I expect the system to reject this name and return the Sign-in page. | Pass | HH, 6/27/2021 | Pass | MS, 7/14/21 | Pass | EL + ZM; 07/22/21
| Given that someone else with my name has signed-in when I enter my name in the Sign-in form and click the Sign-in button then I expect the system to reject my sign-in and return the Sign-in page for me to try a different name. | Pass | JI, 6/27/2021 | Pass | MS, 7/14/21 | Pass | ZM; 07/22/21
| Given that I am signed-in when I navigate to the Home page then I expect to see a list of all other signed-in players. (NOTE: in the next story you will use this list to pick opponents for checkers games.) | Pass | HH, 6/27/2021 | Pass | MS, 7/14/21 | Pass | EL; 07/22/21
| Given that I am not signed-in when I navigate to the Home page then I expect to see a message of how many players are signed-in but not a list of them (for privacy reasons). | Pass | HH, 6/27/2021 | Pass | MS, 7/14/21 | Pass | ZM; 07/22/21
As a Player I want to start a game so that I can play checkers with an opponent. | Given that I'm signed in when I view the Home page then I can start a game by selecting a player listed on the Home page. | Pass | MS, 6/28/2021 | Pass | HH, 7/14/21 | Pass | EL + ZM; 07/22/21
| Given that the player I selected isn't yet in a game when I select that player then the system will begin a checkers game and assign me as the starting (Red) player and my opponent as the White player. | Pass | JI, 6/28/2021 | Pass | HH, 7/14/21 | Pass | EL + ZM; 07/22/21
| Given that the player I selected is already in a game when I select that player then the system will return me to the Home page with an error message. | Pass | ND, 6/28/2021 | Pass | HH, 7/14/21 | Pass | ZM; 07/22/21
| Given that I'm waiting for a game when another player selects a game with me then the system will automatically send me to the Game View as the White player. NOTE: the `home.ftl` HTML includes a `<meta>` tag that tells the browser to refresh the game every 5 seconds; thus you need to update the `GetHomeRoute` controller to handle the situation when a player is assigned a game. | Pass | MS, 6/28/2021 | Pass | HH, 7/14/21 | Pass | EL + ZM; 07/22/21
| Given a valid, initial game board when I drag a piece to a white space then the piece should not be droppable. | Pass | ND, 6/28/2021 | Pass | HH, 7/14/21 | Pass | EL; 07/22/21
| Given a valid, initial game board when I drag a piece to an occupied space then the piece should not be droppable. | Pass | JI, 6/28/2021 | Pass | HH, 7/14/21 | Pass | EL; 07/22/21
| Given a valid, initial game board when I drag a piece to an open space then the piece should be droppable. NOTE: In this Story the drop action should not do anything; piece movement validation will be the focus of future stories. | Pass | MS, 6/28/2021 | Pass | HH, 7/14/21 | Pass | EL + ZM; 07/22/21
| Given a valid, initial game board when I view the board in the browser then my pieces are oriented on the bottom of the board grid just like I would see the board if I were playing in the physical world. | Pass | JI, 6/28/2021 | Pass | HH, 7/14/21 | Pass | EL + ZM; 07/22/21
As a Player I want to be able to resign so that I can end the game when I no longer want to play. | Given that there is a resign button when I clicked the resign button I expect to be able to leave the game. |  |  | Pass | HH, 7/14/21 | Pass | EL; 07/22/21
| Given that the resign button lets me leave the game when I click the resign button, I expect to return to the home page. |  |  | Pass | MS, 7/14/21 | Pass | EL; 07/22/21
| Given that my opponents has the resign button, when they click the resign button, I expect to return to the home page with a message telling me they resigned. |  |  | Pass | MS, 7/14/21 | Pass | EL; 07/22/21; Unable to leave the game when pressing the exit button. HH; 07/25/21
As a Player I want to make a simple move so that I can move my checkers. | Given that I clicked a piece when I click to place my piece on a legal spot then I expect the piece to move. |  |  | Pass | MS, 7/14/21 | Pass | ZM; 07/22/21
| Given that the piece is not a king, when I move the piece to a square behind it, I expect that the piece will not move there. |  |  | Pass | HH, 7/14/21 | Pass | ZM; 07/22/21
| Given that my opponent has made a valid move, when my page refreshes, I expect to see the move they made |  |  | Pass | HH, 7/14/21 | Pass | ZM; 07/22/21
As a Player I want to jump my checkers so that I can capture my opponent’s checkers. | Given that there is an opponent piece between my piece and a empty space, when I drop the piece on the empty space then I expect the piece to have moved to the empty space. |  |  |  |  | Pass | ZM; 07/22/21
| Given that my piece can jump over the opponents piece, when I drop the piece on the empty space, then I expect the opponent's piece to disappear. |  |  |  |  | Pass | ZM; 07/22/21
| Given that I can jump a opponent piece when I move my piece to do so then I expect the space to show as valid |  |  |  |  | Pass | ZM; 07/22/21
| Given that I can jump over my own piece when I move my piece to do so, then I expect the piece to return to its original spot |  |  |  |  | Pass | ZM; 07/22/21
| Given that a piece can jump more than once when I click that piece then I expect to be able to jump more than once. |  |  |  |  | Pass | NJD; 07/25/2021
| Given that my piece is lined up to jump the opponent and another one of my own pieces, when I try to jump both pieces, I expect to only be able to jump the opponent's piece and not my own. |  |  |  |  | Pass | AS; 07/22/21
| Given I am in a position to validly jump three pieces, when I attempt to jump all three, then I expect to jump all three. |  |  |  |  | Pass | ZM; 07/22/21
| Given I am in a position to validly jump N pieces, when I attempt to jump all N pieces, then I expect to jump all N pieces. |  |  |  |  | Pass | ZM; 07/22/21
As a Player I want my piece to be promoted so that I can use the kings ability. | Given that my piece is normal when I move it to the back row then I expect it to be promoted to a king. |  |  |  |  | Pass | AS; 07/22/21
| Given that my piece is a king when I chose to move it then I expect all four directions are available. |  |  |  |  | Pass | AS; 07/22/21
| Given that my piece is a king when I look at it then I expect to be able to tell that it is a king. |  |  |  |  | Pass | AS; 07/22/21
As a Player I want to know when there is a mandatory move so that I know I can't make another move. | Given that I can jump over a piece, when I try to make another move then I expect the piece to return to its original position |  |  |  |  | Pass | NJD; 07/22/2021
| Given that I can jump over multiple pieces, when I jump over one piece then I expect to be unable to submit my turn until I complete the rest of the jumps. |  |  |  |  | Pass | HH; 07/22/2021
| Given that there are no mandatory jumps, when I make a move then I expect the move to be valid |  |  |  |  | Pass | HH; 07/22/2021
| Given that there are two pieces that are able to do a mandatory jump, when I pick a piece, then I expect that piece to complete the mandatory jump. |  |  |  |  | Pass | NJD; 07/22/2021
| Given that there are different routes for the mandatory jump, when I click to jump over one piece instead of the other, then I expect that move to be valid. |  |  |  |  | Pass | HH; 07/22/2021
As a Player I want to know when there are no more moves so that I know I lost the game. | Given that the opponent's move does not allow me to make a move, when it is my turn to make a move, then I expect that the game will end. |  |  |  |  | Pass | NJD; 07/25/2021
| Given that I have the ability to make a move, when it is my turn, then I expect to be able to continue the game. |  |  |  |  | Pass | HH; 07/25/2021
| Given that I make a move that does not allow my opponent to make a move, when I end my turn, then I expect to see the game end. |  |  |  |  | Pass | NJD; 07/25/2021
| Given that my opponent has the ability to make a move, when it is their turn, then I expect the game to continue |  |  |  |  | Pass | HH; 07/25/2021
As a user, I want to be able to join other games even if there are two players so that I can watch them play the game. | Given I want to spectate a game when I attempt to join a game in progress then I join the game as a spectator. |  |  |  |  | Pass | NJD; 07/26/2021
| Given I want to leave when I click exit then I get sent to the home page. |  |  |  |  | Pass | HH; 07/26/2021
| Given I am spectating a game when I attempt to move then nothing should happen. |  |  |  |  | Pass | NJD; 07/26/2021